## Sprint Backlog
PB Name | Task Name | SPRINT NUMBER | Check Out | Status | Remaining Effort [hr]
Login and registration | Implement login and registration service | 1 | Gabriele | Done | 9
Login and registration | Implement Users DB | 1 | Gabriele | Done | 6
Login and registration | Implement Google api access | 1 | Gabriele | Done | 5
Login and registration | Implement terms of service acceptance | 1 | Gabriele | Done | 1
Image storage | Implementation of MinIO endpoint and Communication Setup | 1 | Alessio | Done | 9
Image storage | Implement Image CRUD API | 1 | Alessio | Done | 13
Image storage | JWT-based communication with login service and file preprocessing | 1 | Alessio | Done | 8
Image storage | Testing | 1 | Alessio | Done | 6
Image processing | Implement filter service (filters: gray, blur, canny, dilate, erode, sepia, cartoonify, negative, emboss, sharpen, edge_enhance, rainbowify, mirror, flip, rotate_clockwise, rotate_counterclockwise) | 1 | Placido | Done | 5
Image processing | Testing | 1 | Placido | Done | 3
ELK Stack | Deployment and Internal Orchestration of ELK Stack service | 2 | Gabriele | Done | 18
ELK Stack | Connect ELK Stack service to all other services | 2 | Gabriele | Done | 4
ELK Stack | Add logging endpoints in all the other servivces | 2 | Gabriele | Done | 3
User Interface | Implement main page with orchestration of the microservices (through api calls) | 2 | Alessio | Done | 7
User Interface | Implement images page with preview of all the images | 2 | Alessio | Done | 2
User Interface | Implement aboutus and help pages | 2 | Alessio | Done | 2
User Interface | Integrate all the API calls (after microservice completion) | 2 | Alessio | Done | 3
Use ML model | Training initial model | 2 | Placido | Done | 3
Use ML model | Implement AI model serving | 2 | Placido | Done | 8
Use ML model | Implement loading of latest available model | 2 | Placido | Done | 2
Retrain ML Model | Retrieval of new images from Image Storage | 2 | Placido | Done | 2
Retrain ML Model | Implement retraining logic | 2 | Placido | Done | 4
Retrain ML Model | Upload model to storage | 2 | Placido | Done | 1
Use ML model | Creation of Docker Image for Model Serving | 2 | Placido | Done | 3
Retrain ML Model | Creation of retraining (cronjob) image | 2 | Placido | Done | 2

## Burndown Chart Sprint 1
Date | 2024-03-03 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 28/03 | 29/03 | 2024-04-02 | 2024-04-08 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-15 | 2024-04-19 | 2024-04-21 | 2024-04-22 | 2024-04-25 | 2024-04-28 | 2024-05-01 | 2024-05-02
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Real | 65 | 60 | 58 | 56 | 54 | 51 | 48 | 46 | 42 | 39 | 38 | 36 | 35 | 32 | 30 | 24 | 19 | 16 | 10 | 5 | 0
129 | Remaining Effort [hr]
20 | Number of days in sprint

## Burndown Chart Sprint 2
Date | 23/6 | 28/6 | 29/6 | 30/6 | 2024-07-01 | 2024-02-07 | 2024-06-07 | 2024-07-07 | 2024-07-08 | 21/7 | 2024-07-26 | 2024-07-28 | 2024-08-04 | 2024-08-06 | 2024-08-13 | 17/8 | 20/8 | 24/8 | 29/8 | 30/8
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Real | 64 | 63 | 57 | 51 | 46 | 40 | 37 | 34 | 32 | 28 | 25 | 21 | 17 | 15 | 13 | 11 | 5 | 2 | 1 | 0
129 | Remaining Effort [hr]
19 | Number of days in sprint

## Setup
Product Backlog Status Options | Spring Backlog Status Options | Development Team
Not To Do | To Do | Placido
To Do | Doing | Gabriele
Done | Done | Alessio
OK

## Product Backlog
Task Name | Task Description | Status
Login and registration | Implement Users Database Implement registration and login Implement terms of service acceptance Implement google API access | Done
Image storage | Implement image storage Implement API for retrieving and uploading images | Done
Image processing | Implement filter service Implement help functionality | Done
Retrain ML Model | Implement possibility for admin to retrain ML Model on new data | Done
Use ML model | Implement feedback mechanism for users Implement administrator interface Implement model testing for administrator | Done
User Interface | Implement nice frontend | Done
ELK Stack | Implement admin monitoring of the logs of the site Implement logging endpoints in microservices Collection of data and analytics | Done